# Zero Trust Adoption: Project Charter Template

A phased, five-stage plan for moving from network-perimeter security to an identity-centered Zero Trust architecture — without a rip-and-replace.

Project Information

| Project Name | Zero Trust Adoption Program — [Company Name] |
| --- | --- |
| Executive Sponsor | [Name, Title] |
| Program Lead | [Name, Title] |
| Date Created / Version | [Date] · v[0.1] |
| Charter Status | [Draft / Under Review / Approved] |
| Related Materials | [Link to maturity assessment, stakeholder talking guide, budget request, etc.] |

1. Purpose & Business Case

[Explain, in 2–4 sentences, why this program is being chartered now — e.g. a recent incident, an audit or cyber-insurance requirement, rising identity-based attacks, or a strategic push to reduce risk from hybrid work and third-party access. Reference any supporting data (breach trends, audit findings, board direction) here.]

2. Objectives & Success Measures

- [Objective 1 — e.g. Reduce risk of credential-based breaches by extending phishing-resistant MFA to all privileged and remote users within Phase 1.]

- [Objective 2 — e.g. Eliminate flat VPN access to the top 3 highest-risk applications by end of Phase 3.]

- [Add measurable objectives specific to your organization — tie each to a phase where possible.]

3. Scope

IN SCOPE

- [e.g. All corporate identities (employees, contractors, third parties); crown-jewel applications identified in Phase 0; managed and BYOD endpoints accessing corporate resources.]

OUT OF SCOPE (FOR THIS CHARTER)

- [e.g. OT/ICS environments on isolated networks; systems already scheduled for decommission; physical security controls.]

4. Guiding Principles

These principles apply across every phase and should guide trade-off decisions as the program runs:

- Evolve, don't replace. The firewall, VPN, and existing identity stack stay in place and are progressively wrapped with identity- and context-aware controls, not torn out.

- Sequence by risk and ROI, not by what's easiest to procure. Identity hardening comes first because it delivers the highest risk reduction per dollar with the least user disruption.

- Start narrow, then scale. Each phase begins with one or two crown-jewel use cases before rolling out company-wide.

- Every phase stands on its own. The program should be measurably more secure after each phase, even if it pauses there.

- Zero Trust is an architecture, not a purchase. Grounded in NIST SP 800-207 and the CISA Zero Trust Maturity Model's five pillars — Identity, Devices, Networks, Applications & Workloads, and Data.

5. Phased Roadmap

The default sequence below reflects the standard risk/ROI logic for Zero Trust adoption. Adjust deliverables and exit criteria to your environment, but keep the order — each phase is designed to make the next one lower-risk.

| Phase | Objective | Key Deliverables / Milestones | Exit Criteria (ready for next phase) |
| --- | --- | --- | --- |
| 0 — Assess | Build a risk-ranked inventory to ground the entire roadmap in the organization's actual environment. | • Identity, device, application, and data-flow inventory • Risk-ranked list of crown-jewel apps/data • Gap assessment against the 5 Zero Trust pillars • Approved business case and roadmap | • Inventory validated by stakeholders • 1–2 crown-jewel pilot candidates selected • Roadmap and budget approved by sponsor |
| 1 — Identity | Harden the identity layer first — the highest risk-reduction per dollar and the least disruptive phase. | • Phishing-resistant MFA (passkeys/FIDO2) for priority user groups • SSO consolidated across core applications • Automated joiner-mover-leaver provisioning • Privileged access controls for admin accounts | • MFA coverage target met for priority populations • Access reviews automated • No standing/shared admin credentials outside an approved PAM workflow |
| 2 — Device | Add device posture and contextual risk signal to access decisions, closing the BYOD/unmanaged-device gap. | • Device posture checks integrated into access flows • Conditional access combining identity + device + risk • Managed-device or compliant-BYOD enrollment path | • Conditional access enforced for priority applications • Non-compliant devices blocked or restricted from sensitive resources |
| 3 — Segment | Replace flat VPN access with per-application Zero Trust Network Access (ZTNA), starting narrow. | • ZTNA deployed for the 2–3 crown-jewel apps identified in Phase 0 • Legacy VPN access scoped down for migrated users • Lateral-movement monitoring for segmented zones | • Pilot applications fully migrated off flat network access • No regression in user experience or performance • Measurable reduction in standing network access |
| 4 — Verify | Mature from “verify at login” to continuous, real-time verification — including non-human identities. | • Real-time risk scoring and automated response • Data-level access controls for sensitive data sets • Governance extended to service accounts, API keys, and AI agents | • Continuous verification live for priority applications • Non-human identity inventory under active governance • Automated response playbooks tested |

6. Execution Tracker

Update as the program runs. This is the working view for status reporting to the steering committee.

| Phase | Owner | Target Start | Target End | Status | Notes |
| --- | --- | --- | --- | --- | --- |
| 0 — Assess | [ ] | [ ] | [ ] | Not Started | [ ] |
| 1 — Identity | [ ] | [ ] | [ ] | Not Started | [ ] |
| 2 — Device | [ ] | [ ] | [ ] | Not Started | [ ] |
| 3 — Segment | [ ] | [ ] | [ ] | Not Started | [ ] |
| 4 — Verify | [ ] | [ ] | [ ] | Not Started | [ ] |

7. Roles & Governance

| Role | Responsibilities | Name / Owner |
| --- | --- | --- |
| Executive Sponsor | Owns the business case, secures budget, removes organizational blockers, approves phase gates. | [ ] |
| Program Lead | Runs the roadmap day-to-day, tracks phase progress, reports to the steering committee. | [ ] |
| Identity / IAM Lead | Owns Phase 1 and identity-layer decisions across all subsequent phases. | [ ] |
| Network / Security Architecture Lead | Owns firewall and network-segmentation continuity and leads the Phase 3 ZTNA rollout. | [ ] |
| Application Owners | Provide crown-jewel application context, validate exit criteria, coordinate migration windows. | [ ] |
| Steering Committee | Reviews phase-gate decisions and approves progression to the next phase. | [ ] |

Governance cadence: [e.g. Steering committee meets biweekly during active phases and monthly during stabilization; phase-gate sign-off required from the Executive Sponsor before starting the next phase.]

8. Risks & Assumptions

A few common risks are pre-filled as a starting point — add organization-specific entries below them.

| Risk / Assumption | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| New MFA / access methods create user friction and slow adoption. | Medium | Medium | Phase MFA rollout by user group; communicate early; offer a low-friction method (passkeys) before enforcing broadly. | [ ] |
| Legacy, OT, or IoT systems can't support modern identity agents. | Medium | High | Keep these systems behind existing network segmentation (firewall) rather than forcing them into Phase 1–2 scope. | [ ] |
| Third-party / vendor accounts fall outside standard identity lifecycle automation. | High | Medium | Extend joiner-mover-leaver automation to a defined third-party access process in Phase 1. | [ ] |
| [Add organization-specific risk or assumption] | [ ] | [ ] | [ ] | [ ] |
| [Add organization-specific risk or assumption] | [ ] | [ ] | [ ] | [ ] |

9. Budget & Resource Considerations

| Phase | Primary Resource Needs | Budget Notes |
| --- | --- | --- |
| 0 — Assess | Discovery/assessment tooling or consulting time; program lead bandwidth. | [ ] |
| 1 — Identity | MFA/passkey licensing, SSO consolidation effort, identity governance tooling. | [ ] |
| 2 — Device | Device management/posture tooling, conditional access policy engine. | [ ] |
| 3 — Segment | ZTNA licensing, migration effort for pilot applications. | [ ] |
| 4 — Verify | Risk-scoring/automation tooling, non-human identity governance. | [ ] |

[Add total estimated budget, funding source, and any procurement dependencies — e.g. existing IAM/MDM contracts that may cover part of Phase 1–2 at no additional cost.]

10. Communication Plan

- [e.g. Steering committee: written status update biweekly, live review at each phase gate.]

- [e.g. Broader stakeholders/department heads: summary update at the close of each phase.]

- [e.g. End users: advance notice and instructions before any change that affects login (Phase 1 MFA rollout) or device enrollment (Phase 2).]

11. Approval & Sign-off

This charter authorizes the program to begin Phase 0. Progression into each subsequent phase requires Executive Sponsor sign-off against the exit criteria in Section 5.

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| [ ] | Executive Sponsor | [ ] | [ ] |
| [ ] | IT / Security Leadership | [ ] | [ ] |
| [ ] | Program Lead | [ ] | [ ] |
| [ ] | [Additional Approver] | [ ] | [ ] |

About the Contributing Author

Contributed by Cliff Varnadoe, Director, US Federal & Enterprise of SonicWall for Logically’s cybersecurity summit, LogicON.

About Logically

Close the Gap with Logically, the Next-Gen MSP Logically unifies IT operations and cybersecurity into one accountable operating model, providing shared visibility, coordinated response, and clearer control. Modern IT and multi-layered security from one partner, built into an integrated operating model that attackers can’t exploit and traditional MSPs can’t match.

Visit www.logically.com to learn more.